## Timeline OSH
Date | Time: | Chronology of events | Thursday 24th February | Friday 25th February | Saturday 26th February |  | Sunday 27th February | Monday 28th February | Tuesday 1st March | Wednesday 2nd March | Thursday 3rd March
Tuesday, March 23, 2021 |  | Scope of Works developed for contract for Miscellaneous Repairs and Refurbishment Works at #5 & #6 Berths, Main Viaduct and Servicing of Mooring Buoys
Thursday, April 15, 2021 |  | Scope of Work reviewed by Technical and Maintenance Dept
Thursday, April 29, 2021 |  | SCM issued ITB document to potential bidders
Friday, April 30, 2021 |  | ITB Invitation date
Tuesday, May 4, 2021 |  | A mandatory virtual Site Visit Meeting was held for invited contractors. Any contractor that failed to attend the virtual Site Visit was disqualified.
Monday, May 10-11, 2021 |  | In-person Site Visits were held for invited contractors
Thursday, May 13, 2021 |  | Clarification Period Close
Friday, May 14, 2021 |  | Paria's response to Clarification for contractors
Tuesday, May 18, 2021 |  | Contractors were required to submit their bids by 2021 May 18 and bids were opened
Wednesday, May 19, 2021 |  | The Technical Submissions in the Bids were evaluated by T&M, and the Tender was awarded to LMCS Limited.
Tuesday, June 1, 2021 |  | PO 4500627840 was signed by Paria and LMCS
Wednesday, June 2, 2021 |  | Pre-work started
Tuesday, June 29, 2021 |  | Paria held a Kick-off (Pre-mobilisation) Meeting with LMCS to discuss the way forward for the Repairs to # 36 SL Riser @ Berth # 6.
Friday, July 2, 2021 |  | A serious accident occurred at LMCS Yard while work was being done on this contract at Offshore Services Dock at Paria which resulted in critical injury to LMCS employee Sunil Soodhan.
Tuesday, July 06, 2021 |  | OSH Agency issued a Prohibition Notice to Paria prohibiting all pile and riser fabrication works on this contract until the relevant dangers were removed and the Notice has been complied with.
2021 Jul – 2021 Dec |  | Paria implemented measures to ensure a safe system of work and to address the existing dangers. OSH Inspectors conducted site visits and document reviews to determine whether works can be restarted and safely executed.
Wednesday, October 13, 2021 |  | Pre-Restart of 36 SL Repairs meeting and the agenda is as follows: •To discuss work completed •What pre-work needs to be done and the way forward •Draining options •Any outstanding material issues •Update schedule •Additional HSE requirements •Any other concerns
Wednesday, January 5, 2022 |  | OSH Agency issued a Certificate of Compliance to Paria stating that Paria has complied with the Prohibition Notice. OSH Inspections were conducted on 2021 Sep 10, 2021 Oct 22, 2021 Nov 10, 2021 Nov 26 and 2022 Jan 04 to verify the implementation of the necessary measures.
Friday, January 7, 2022 |  | Work resumed on SOW both at OSSD and Offshore:36 SL Riser-Clearing of concrete around 30" pipe underwater
Monday, January 10, 2022 |  | Work done - 36 SL Riser- Clearing of concrete around 30" pipe underwater, Hot bolt topside piping
Tuesday, January 11, 2022 |  | Work done - 36 SL Riser-Clearing of concrete around 30" pipe underwater, Hot bolt topside piping
Wednesday, January 12, 2022 |  | Work done - 36 SL Riser-Clearing of concrete around 30" pipe underwater, Hot bolt topside piping
Thursday, January 13, 2022 |  | Work done - 36 SL Riser-Clearing of concrete around 30" pipe underwater
Monday, January 17, 2022 |  | Work done - 36 SL Riser-Clearing of concrete around 30" pipe underwater, Removal of 12" slip blank on S/L 36 manifold
Tuesday, January 18, 2022 |  | Work done - Phase 1 Air Blowing from Berth 5 to 6 - Air blowing contents of S/L 36 from berth 5 to 6 into S/L 66
Thursday, January 20, 2022 |  | Work done - Phase 1 Air Blowing, from Berth 5 to 6 - Air blowing contents of SL 36 from berth 5 to 6 into SL 66
Friday, January 21, 2022 |  | Work done - Air blowing contents of S/L 36 from berth 5 to 6 into slops, Installation of 12" slip blank on S/L 36 manifold
Friday, January 21, 2022 |  | Work done - OSSD- Removal of pile from fabrication bed and place onto barge
Saturday, January 22, 2022 |  | Work done - Phase 1 Air Blowing, from Berth 5 to 6 - Air blowing contents of S/L 36 from berth 5 to 6 into slops barge
Sunday, January 23, 2022 |  | Work done - Berth 6 - Installation of riser support pile
Tuesday, January 25, 2022 |  | Work done - Berth 6 - Installation of riser support pile
Thursday, January 27, 2022 |  | Work done - Berth 6 - Installation of riser support pile
Friday, January 28, 2022 |  | Work done - Refurbished chamber at Offshore Services Dock (OSSD) for use on riser
Saturday, January 29, 2022 |  | Work done - Refurbished chamber at Offshore Services Dock (OSSD) for use on riser
Monday, January 31, 2022 |  | Work done - Refurbished chamber at Offshore Services Dock (OSSD) for use on riser
Monday, January 31, 2023 |  | Work done at Berth 6 - Removed topside piping, installed solid blank on piping going into berth, installed flange with boss on both sides with 6" hose into riser for Phase 2 air blowing
2022-02-01 |  | Work done - Phase 2 Air blowing contents of Sealine 36 from Berth 5 to Berth 6 into Sealine 66.
2022-02-01 |  | Work done - Refurbished chamber at Offshore Services Dock (OSSD) for use on riser
2022-02-03 |  | Work done - Phase 2 Air blowing contents of Sealine 36 from Berth 5 to Berth 6 into Sealine 66.
2022-02-03 |  | Work done - Refurbished chamber at OSSD for use on riser. Grit blast topside piping from Berth #6
2022-02-05 |  | Work done - Berth 6 - Removal of piping from SL 36 to SL 66, Soft bolting of topside piping
2022-02-05 |  | Work done - Fabrication of new topside piping at OSSD
2022-02-10 |  | Work done - Fabrication of new topside piping at OSSD
2022-02-10 |  | Work done - Cut riser clam and jack hammer concrete sleeve around riser, Removal of topside piping and solid blank ends at Berth 5
2022-02-11 |  | Work done - Fabrication of new topside piping at OSSD
2022-02-11 |  | Work done - Cut section of riser and weld new flange at Berth 5
2022-02-12 |  | Work done - Fabrication of new topside piping at OSSD
2022-02-13 |  | Work done - Remove solid blank from existing riser, install plug and migration barrier, cut clamp around riser, cut and remove old riser support, install chamber, weld support from chamber onto new support pile at Berth 6.
2022-02-14 |  | All safety checks was conducted for use of hyperbaric chamber at Berth 6
2022-02-14 |  | Teams Meeting held between Paria and LMCS to discuss (i) works scheduled to be executed for 2022/02/14 to 2022/02/19 and (ii) to address any concerns for the repairs of 36 SL Riser. |  |  |  | PARIA
2022-02-14 |  | Work done - Fabrication of new topside piping at OSSD |  |  |  | LMCS
2022-02-15 |  | Work done - Fabrication of new topside piping at OSSD
2022-02-15 |  | Work done - Installation of 30" subsea slip-on flange at Berth 6
2022-02-16 |  | Work done - Soft bolt 50" flange on top of hyperbaric chamber at Berth 6
2022-02-16 |  | Work done - Fabrication of new topside piping. Grit blast topside piping for berth #6 at OSSD
2022-02-17 |  | LMCS failed to comply with a PTW requirement when they mobilized the crane barge without a signed Work Permit and certified Hot Work. Paria suspended all work due to the infringement and arranged a Contractor Intervention Session with LMCS to address the safety non-conformance.
Monday, February 7, 2022 to Tuesday, February 22, 2022 |  | LMCS conducted an investigation into the breach and implemented the recommendations from their investigation. Paria accepted the recommendations and LMCS was given the okay by T&M and HSE to recommence work.
2022-02-24 | 1000 - 1030hrs | Onsite Meeting held at OSSD at LMCS Conference room between LMCS (Kazim Ali Snr, Kazim Ali Jnr, Ahmad Ali) and Maintenance Planner (T Rampersadsingh). The planned schedule of work for weekend activities were discussed and outlined as follows: Friday 2022 Feb 25th: • Remove old riser section from hyperbaric chamber • Install new riser section in hyperbaric chamber • Hydrotest installed flange on riser • Couple new riser section to riser flange and guarantee flange Saturday 2022 Feb 26th: • Remove hyperbaric chamber from riser Sunday 2022 Feb 27th: • Install top side piping and take measurements for installation of Slip-On flange • Cut and install Slip-On flange • Carry out inspection requirements
2022-02-24 | 1315hrs | Terrance Rampersadsingh spoke with Paria offshore operations team on the agreed works.
2022-02-24 | 1430hrs | Terrance Rampersadsingh spoke with Paria offshore maintenance team on the agreed works.
2022-02-25 |  | At this point the chamber was in place over #36 sealine riser, the compressor was off, the 2.5” vent at the top was open as it usually is, within the chamber was equal to atmospheric conditions, sea water level was higher than the top of the riser, and the solid blank on top of the riser was in place preventing water from entering the riser. The old riser piece that had been cut off was inside the chamber and was securely rigged to the chamber walls with two chain hoists. The 50” flange which is the chamber cover was bolted in place at the top of the chamber.
2022-02-25 | 0730hrs | Paria issued permits to LMCS to remove and install 50” flange, remove and install 30” riser pipe, remove 30”solid blank, conduct pressure test on flange weld, remove chamber and blank on top new riser
2022-02-25 | 0800hrs | A toolbox meeting commenced on LMCS's barge and was led by Mr. Victor Dhillpaul (LMCS HSE Officer) and Mr. Kazim Ali Jr.. The tasks (Removal of old cut off section, installation of new section and secure same inside the chamber, blowdown of the chamber, installation of the camera/lighting, removal of solid blind flange, carber plug testing and possibly installation of the new spool piece and removal of the hyperbaric chamber).
2022-02-25 | 0800 - 0930hrs | A. Dopson (HSE) assessed the barge hot work areas (the compressor and crane barge) to confirm that all hot work conditions were in place and certified the Hot Work Certificates. He informed the Offshore OTS (J Ramdhan) that the Hot Work Certificates were certified and that LMCS had clearance to use the compressor and the crane. The LMCS workers proceeded to their respective work areas at Berth 6 and Berth 5. Berth 6 - The cover of the chamber was unbolted and removed. Berth 6 - The old riser piece was removed using the crane and placed on the crane barge. Berth 6 - LMCS’ workers rigged the new spool piece for the riser, lifted it with the use of the crane into the chamber and secured it inside the chamber. Berth 6 - The cover of the chamber was re-installed and bolted by LMCS employees
At this point, LMCS was ready to reduce the level of water in the chamber so that they could access the flange at the top of the riser to do the planned weld hydrotest. To reduce the water level, they started the compressor which displaced the water from the chamber. LMCS had arranged for hydrostatic weld testing to be done by their sub-contractor ISOTECH Ltd. using a Carber plug testing method. LMCS plan was for the tests to be conducted on the weld neck flange at Berth 5 (above sea level) first and then on the slip-on flange at Berth 6 sub-sea within the chamber. LMCS had arranged for the testing activities to commence at 1000hrs.
2022-02-25 | 0930hrs | Berth 6 - The compressor was started and run to “blow down” the water in the chamber. Atmospheric testing was conducted by Paria HSE (A. Dopson) at the 2.5" vent valve which was located on the top cover of the chamber. The readings were as follows: H2S - 0ppm, CO - 0ppm , SO2 - 0ppm, LEL - 0ppm, VOC – 8ppm, O2 - 20.9%
2022-02-25 | 0940hrs | Berth 6 – A Dopson continued to monitor the vent until the VOC values decreased to zero and were consistently zero. This steady state was observed by 0940 hrs. All other parameters remained unchanged. Clearance was then given to the LMCS employees to enter the chamber based on the air quality readings.
2022-02-25 | 0955hrs | Berth 6 - Three LMCS employees (Fyzal Kurban, Yusuf Henry and Rishi Nagassar) entered the water and the chamber to do water level checks. The LMCS employees assessed the chamber conditions and determined that it was safe to enter the chamber to work. The lighting and camera were then installed in the chamber.
2022-02-25 |  | Berth 6 - While within the chamber, the LMCS employees removed the 30” blind flange from the flange on the top of the riser in preparation for hydrostatic testing of the weld.
2022-02-25 |  | Berth 6 - The three LMCS employees exited the chamber. A. Dopson
2022-02-25 | 0830-1000hrs | LMCS employees proceeded to Berth 5 to prepare for Carber testing of the 30” riser flange neck (this is located above sea level). They removed the blind flange and awaited the arrival of the LMCS sub-contractor ISOTECH Ltd.
2022-02-25 | 1000hrs | LMCS (Dexter Guerra) contacted A Ramlogan and informed him that ISOTECH employees were on site and ready to conduct Carber testing. A Ramlogan met the ISOTECH team at Offshore Services Dock.
2022-02-25 | 1000 - 1130hrs | A Ramlogan and the LMCS sub-contractor ISOTECH left Offshore Services Dock and arrived at Berth 5 via LMCS pirogue. The blank flange was already removed so ISOTECH proceeded to carry out the Carber test on the weld neck. Work Permit – No. 9327
2022-02-25 | 1130-1145 hrs | The Carber test at Berth #5 commenced at 1130 and was completed by 1145 hrs.
2022-02-25 |  | The ISOTECH employees and Adesh Ramlogan then boarded the pirogue and were transported to Berth 6.
2022-02-25 | 1200 - 1345hrs | A Ramlogan and the ISOTECH employees arrived at Berth 6 to carry out hydrostatic weld testing using the Carber plug. The plan was for the ISOTECH personnel to stay on the barge while they guided the LMCS personnel within the chamber on how to carry out the hydrostatic test. Three LMCS employees (Fyzal Kurban, Yusuf Henry and Rishi Nagassar) entered the water and re-entered the chamber to take measurements of the riser top to determine if the hydrostatic testing could be done. It was discovered that the pipe below the flange was not circular which meant that the Carber equipment would not seal properly and as such the test could not be done. A. Dopson, A Ramlogan and the ISOTECH crew returned to shore
2022-02-25 | 1330hrs | Berth 5 – The blind flange at Berth 5 was reinstalled by LMCS employees
2022-02-25 | 1338hrs | Berth 6 – LMCS suspended dive operations at Berth 6 and all divers (Fyzal Kurban, Yusuf Henry and Rishi Nagassar) exited the chamber and the water and returned topside.
2022-02-25 | 1415hrs | Five (5) divers entered the chamber. Kazim Ali, Rishi Nagessar, Yusuf Henry, Fyzal Kurban, Christopher Boodram.
2022-02-25 | 1430hrs | The LMCS employees removed the mechanical plug from the #36 Sealine riser. Note - It is not known if the mechanical plug was removed before or after 1415hrs
2022-02-25 |  | The LMCS employees commenced deflating the inflatable plug.
2022-02-25 |  | The chamber flooded with water and the water entered the 30” pipeline resulting in all five (5) LMCS employees being drawn into the pipeline.
2022-02-25 | 1445hrs | A splash was observed by Offshore Operator K Scott (Kenson) on the camera and monitoring screen went black.
2022-02-25 |  | Alarm raised to LMCS Dive Supervisor, Onsite LMCS Supervisor and LMCS safety personnel. LMCS emergency back up plan initiated
2022-02-25 | 1450hrs | OTS informed
2022-02-25 | 1455-1510hrs | LMCS dive supervisor donned gear, as no rescue diver was available and conducted two dives into the chamber and reported no sign of divers or equipment
2022-02-25 | 1510hrs | Paria started sea search and rescue.
2022-02-25 | 1540hrs | Paria informed Coast Guard and commenced informing all other relevant authorities. All vessels informed to stay clear of harbour.
2022-02-25 | 1640hrs | Coast guard arrived and assisted with sea search and rescue. Coast Guard indicated that they were not able to enter the water/chamber due to unknown conditions.
2022-02-25 | 1650hrs | Kazim Ali Snr was requested to send a representative from LMCS for the IMT to provide information about the job and the incident. He said that he would arrange the same
2022-02-25 | 1710hrs | Paria HSE heard knocking within chamber and established communication. Awaiting LMCS rescue divers.
2022-02-25 | 1736hrs | Christopher Boodram retrieved by LMCS divers. Diving operations continued
2022-02-25 | 1740hrs | Paria EMT attended to rescued diver. Dispatched to SFGH
2022-02-25 | 1815hrs | LMCS Dive Supervisor requested assistance with refilling scuba air tanks and escort for additional LMCS divers and diving equipment
2022-02-25 | 1824hrs | Paria requested coast guard to refocus operations for dive rescue within the pipeline. Coast Guard indicated that the required resources were en route.
2022-02-25 | 1900hrs | Paria instructed that diving should be suspended due to unknown cause of incident, unknown conditions within pipeline and endangering personnel
2022-02-25 | 1915hrs | LMCS diving operations still ongoing
2022-02-25 | 1930hrs | PISL Borescope arrived and dispatched to berth 6, however, insufficient lighting for pipeline inspection
2022-02-25 | 1930hrs | Additional LMCS and other divers arrive on site
2022-02-25 | 1937hrs | ROV sourced, however, upon communication with LMCS Dive supervisor, he indicated the ROV was too big to enter
2022-02-25 | 1945hrs | LMCS confirmed to Paria that they had informed the families of the incident.
2022-02-25 | 2000hrs | Paria refilled five of LMCS scuba tanks
2022-02-25 | 2100hrs | Paria explored if incident caused by Delta P across chamber and pipeline
2022-02-25 | 2103hrs | Coast Guard did not consider diving safe and inquired about alternate rescue plans
2022-02-25 | 2106 - 2200hrs | LMCS requested that riser spool be installed at Berth no 6. Paria agreed. Divers dispatched and riser spool installed by 2200hrs
2022-02-25 | 2158hrs | Paria communicated with C. Boodram via telephone to gather information to further inform rescue plans.
2022-02-25 | 2242hrs | Push rod camera arrived on site. Awaiting completion of scaffolding for deployment
2022-02-25 | 2339hrs | Hull Diving Support confirmed they will not perform rescue
2022-02-25 | 2350hrs | Paria informed by Coast Guard that they will not dive
2022-02-26 | 2400hrs-0020hrs | Push rod Camera showed line filled with sea water, no air pockets and an air tank which prevented going further.
2022-02-26 | 0056hrs | Push rod Camera findings shared with coast guard and two (2) commercial diving companies (OTSL and Mitchell Divers). All indicated they will not perform any dive due to the risks involved
2022-02-26 | 137hrs | Eastern Divers and HHSL rescue teams arrived and were asked to explore confined space rescue options.
2022-02-26 | 137hrs | HHSL pipeline crawler/camera team arrived and dispatched to Berth 6
2022-02-26 | 0337hrs | Paria commenced mobilization of two(2) IOCL pumps for berth 5 and berth 6
2022-02-26 | 0316 - 0424hrs | HHSL Crawler inspection at Berth 6 commenced and confirmed line filled with water and no air pockets and scuba tank. Multiple attempts to move scuba tank were futile
2022-02-26 | 0500hrs | Paria IMT decided to remove blind flange at berth 5 and conduct crawler inspection
2022-02-26 | 0600hrs | HHSL Crawler inspection at Berth 5 revealed oil at bottom of riser. Crawler heavily soiled and unable to continue.
2022-02-26 | 0745- 0800hrs | IOCL centrifugal pumps and equipment arrived at gate and dispatched to lube oil jetty.
2022-02-26 | 0750hrs | Lorena B to create ullage for receipt of oil from Berth 5
2022-02-26 | 0800hrs | Paria continues to explore other pumping options inclusive of submersible sump pump.
2022-02-26 | 0830hrs | Paria explores option of subsea cutting of no. 36 sealine with IOCL.
2022-02-26 | 0945hrs | LMCS Project Manager met with IMT and indicated there was a bar across the topside riser spool. Removal of hyperbaric chamber required in order to cut and remove the bar
2022-02-26 | 1000hrs | Paria attempted to meet with the families at PAP staff club. However to facilitate the meeting, families had some requirements that Paria had to meet.
2022-02-26 | 1100hrs | Hiab truck arrived to lift IOCL pumps onto vessel.
2022-02-26 | 1131hrs | Paria informs and receives authorization from OSH Agency for removal of Hyperbaric Chamber.
2022-02-26 | 1200hrs | Requested an operator to conduct a dip of the line
2022-02-26 | 1200hrs - 0106hrs | Paria met and apprised the families at PAP staff club. Agreed communication protocols were set up. Families declined EAP support from Paria.
2022-02-26 | 1436 - 1600hrs | Paria consulted internally to discuss status of ongoing rescue attempts & considered recovery options
2022-02-26 | 1419 - 1721hrs | IOCL Pumps arrived aboard Carib Valley.1 IOCL pump sited on Berth 6 and other pump sited on LMCS Barge.
2022-02-26 | 1630hrs | Paria & LMCS met at the ICC & agreed to move efforts from rescue to recovery & to meet with & advise the families accordingly in person.
2022-02-26 | 1700hrs | Two (2) Laing centrifugal vacuum assisted pumps identified and mobilization commenced
2022-02-26 | 1730-1830hrs | Paria & LMCS visited the first family to inform of the move from rescue to recovery efforts. Due to response from family, LMCS's decision not to continue. Communication reverted to earlier agreed communication protocol
2022-02-26 | 2045hrs | LMCS Commenced removal of Hyperbaric chamber
2022-02-27 | 0341hrs | Hyperbaric Chamber, Cable and Boom fell into sea. NO INJURIES REPORTED
2022-02-27 | 0900hrs | LMCS Mr Ali and diving team arrived on site to discuss retrieval dive.
2022-02-27 | 1000hrs | Replacement crane barge (Seabass ) arrived.
2022-02-27 | 1200hrs | Risk assessment process on dive retrieval commenced
2022-02-27 | 1300hrs | Transfer of vacuum assisted pump to Carib Valley at berth 5 completed
2022-02-27 | 1400hrs | Planning meeting to start fabrication of discharge and bypass valve manifold to conduct a water displacement exercise from Berth 5 to Berth 6 using salt water the Laing pump on the tug Carib Valley. The water displacement exercise involved the use of 2 diesel driven pumps (1 main and spare) on board the Carib Valley tub located at #5 Berth to pump saltwater at a controlled rate into 36 Sealine riser, through a fabricated spool equipped with a bypass valve and discharge valve to carefully and respectfully control the water being displaced.
2022-02-27 | 1404hrs | Borescope Video footage provided to LMCS for a risk assessment for a dive operation by LMCS.
2022-02-27 | 1508hrs | Filling the riser at Berth 5 commenced
2022-02-27 | 1649hrs | Decision made after consultations that a diver would not be sent into berth 6 due to risk involved.
2022-02-27 | 1650hrs | First phase of scaffold on berth 6 complete. Process of cutting of steel bar in progress
2022-02-27 | 1651hrs | Boom placement in progress
2022-02-27 | 2100hrs | Team performed a risk assessment and finalised operation procedure for a water displacement exercise using the inflatable plug that was already in the line.
2022-02-28 | 0530hrs | Walkdown conducted to ensure that all site preparations were made at the risers on Berth 5 and Berth 6. Valve manifold and the scaffolding to access the riser at Berth 5 as well as the scaffolding at Berth 6 required adjustments. Liquid level on Berth 5 was lower than that was previously filled to and that the level at Berth 6 had risen.
2022-02-28 | 0730hrs | Team re-evaluated the risk assessment given the changed conditions of the 36 Sealine riser liquid levels overnight.
2022-02-28 | 0900hrs | Onsite Adjustments completed
2022-02-28 | 1045hrs | Vacuum assisted pump at Berth 5 started.
2022-02-28 | 1125hrs | Water emitting from Berth 6 riser.
2022-02-28 | 1148hrs | First hose connection failure
2022-02-28 | 1156hrs | Osei (Heritage) indicated that Heritage Oil Spill vessel, the Antique is on site and situated 1 mile west of berth 6
2022-02-28 | 1200hrs | All Operations paused as there was unauthorized access in the area. Drone flying over the riser at berth 6.
2022-02-28 | 1213hrs | Operations resumed after drone flew off in the direction of Flower Pot
2022-02-28 | 1214hrs | Hose failure
2022-02-28 | 1244hrs | HHSL deployed their crawler at Berth 6 to check for movement of objects within the pipe.
2022-02-28 | 1317hrs | A rope and scuba tank were observed along the horizontal section of 36 Sealine. Crawler was taken out.
2022-02-28 | 1420hrs | Pumping operations resumed
2022-02-28 | 1429 hrs | Operations paused as a hose coupling came off
2022-02-28 | 1455hrs | Crawler re-deployed and the scuba tank moved closer to Berth 6.
2022-02-28 | 1745hrs | Water displacement operations resumed with the adjustments being made on pump’s (located on Carib Valley) speed and valve positions at Berth 5 based on the appearance of the flow exiting the riser.
2022-02-28 | 1750hrs | Oily water, diving gloves and a scuba tank followed by the bodies of the three divers in sequence (1st at 5.53pm) and then other diving equipment.
2022-02-28 | 1758hrs | S.Chadee of the MEEI was formally notified for spill around berth 6 while on location at the incident command room by R. Archbald
2022-02-28 | 1801hrs | Shevon Ali Chief Inspector OSH agency formally notified of the recovery of three bodies surfacing at no 6 berth and that they are being retrieved by the coast guard at this time. Informed of slight sheen which is being dispersed mechanically
2022-02-28 | 1850hrs | Water displacement operation was re-started, quickly ramping up the pressure to minimize the oily water effluent however oil was seen emitting from riser and the pump speed was at its maximum with only 30psig on its discharge. Pumping operations were then aborted as no more movement was possible as the inflatable plug was either deflated or too much clearance existed between the pipe walls and the inflatable plug.
2022-02-28 | 2130hrs | Planning meeting held to discuss removal of oil from the pipe but the following constraints existed: Lorena B could only fit at Berth 5 due its size and that the Slops barge can take only 80 bbls at a time. ICT requested that a larger slops vessel (but smaller than the Lorena B) be sourced to use at Berth 6. The other option would be to discharge the oily salt water into 66 Sealine leading to potential integrity issues as well as having a commercial impact on crude loading. After a lengthy discussion, the team decided to pump from Berth 5 to the Lorena B.
2022-03-01 | 0815hrs | Planning meeting on water displacement device
2022-03-01 | 0930hrs | NGC conducting site visit
2022-03-01 | 1600hrs | Crawler was deployed and various objects and oil was seen. At around 5pm, at 700ft tether length, diving equipment was observed entangled.
2022-03-01 | 1900hrs | Crawler was deployed at Berth 5. Crawler went in to approximately 120ft before too much oil was seen on the bottom of the crawler tracks.
2022-03-01 | 2030hrs | Planning meeting held to discuss a plan using the water displacement device from Berth 6 and discharging into the Lorena B as no other vessel was available to do the reverse and fit at Berth 6. This required the welding of a flange at Berth 6 riser, a valve manifold arrangement, a startup strainer. Arrangements were put in place for the fabrication / sourcing of material to occur during the night.
2022-03-02 | 0830hrs | Planning meeting held and Vessel Sea Manatee, having a nominal capacity of 1000bbls was confirmed to have been sourced. Arrangements made to have the Higher head multi speed vacuum assisted pump used at Berth 5 and higher volume multi speed vacuum assisted pump used to take suction from Berth 6.
2022-03-02 | 1300hrs | Team performed risk assessment for a water displacement exercise from Berth 5. In parallel, executed modifications to the suction strainer. The operations procedure was also updated to reflect the change of using 2 pumps during the water displacement device.
2022-03-02 | 1900hrs | Sea Manatee arrived at Berth 6
2022-03-02 | 2100hrs | Vacuum assisted pump at Berth 5 started.
2022-03-03 | 0039hrs | 4th Body Recovered
2022-03-03 | 0145hrs | Pumping at Berth 5 was restarted to retrieve the water displacement device. Same was retrieved at 2am and the pump was shutdown.
2:30pm
3:30pm
4:30pm
4:00pm
3:30am
1:30am
12:30am
11:30pm
10:30pm
9:30pm
8:30pm
5:30pm
5:30am
4:30am
2:45pm
Incident Occurs
2:55pm - 3:10pm- LMCS dive supervisor donned gear, as no rescue diver was available and conducted two dives into the chamber and reported no sign of divers or equipment
3:10PM
Paria started sea search
and rescue.
2:30am
4:55pm- Three LMCS divers arrived via a pirogue. Diving operations resumed from 5:30pm.
5:36 pm- Christopher Boodram retrieved by LMCS divers. Diving operations continued
6:24pm
Paria requested coast guard to refocus operations for dive rescue within the pipeline. Coast Guard indicated that the required resources were en route.
3:40pm
Paria informed Coast Guard and relevant authorities. All vessels informed to stay clear of harbour.
8:00pm
Paria refilled five of LMCS scuba tanks
7:37pm
ROV sourced, however, upon communication with LMCS Dive supervisor, he indicated the ROV was too big to enter
9:06 - 10:00pm- LMCS requested that riser spool be installed at Berth no 6. Paria agreed. Divers dispatched and riser spool installed by 10pm
10:42pm
Push rod camera arrived on site. Awaiting completion of scaffolding
11:50pm
Paria informed by Coast Guard that they will not dive
12:00am-12:20am Push rod Camera showed line filled with sea water, no air pockets and an air tank which prevented going further.
1:37am
Eastern Divers and HHSL rescue teams arrived and were asked to explore confined space rescue options.
3:37am
Paria commenced mobilization of two(2) IOCL pumps for berth 5 and berth 6.
6:30am
3:16am - 4:24am
HHSL Crawler inspection at Berth 6 commenced and confirmed line filled with water and no air pockets and scuba tank. Multiple attempts to move scuba tank were futile
5:00am
Paria IMT decided to remove blind flange at berth 5 and conduct crawler inspection
2:15pm
LMCS Divers entered positive pressure Chamber
5:10pm
Paria HSE heard knocking within chamber and established communication. Awaiting LMCS rescue divers.
7:30pm- Additional LMCS divers arrived on site
5: 40 pm
Paria EMT attended to rescued diver. Dispatched to SFGH
6:15pm- LMCS Dive Supervisor requested assistance with refilling scuba air tanks and escort for additional LMCS divers and diving equipment
6:00pm
6:30pm
5:00pm
7:00pm
7:00pm
Paria instructed that diving should be suspended due to unknown cause of incident, unknown conditions within pipeline and endangering personnel
4:40pm
Coast guard arrived and assisted with sea search and rescue. Coast Guard indicated that they were not able to enter the water/chamber due to unknown conditions.
1139pm
Hull Diving Support confirmed they will not perform rescue
9:00pm
Paria explored if incident caused by Delta P across chamber and pipeline
12:56am Push rod Camera findings shared with coast guard and two (2) commercial diving companies (OTSL and Mitchell Divers). All indicated they will not perform any dive due to the risks involved
1:37am
HHSL pipeline crawler/camera team arrived and dispatched to Berth 6
7:15pm- LMCS diving operations continues
7:30pm
PISL Borescope arrived and dispatched to berth 6, however, insufficient lighting for pipeline inspection
9:58 pm
Paria communicated with C. Boodram via telephone to gather information to further inform rescue plans.
6:00am
HHSL Crawler inspection at Berth 5 revealed oil at bottom of riser. Crawler heavily soiled and unable to continue.
7:45- 8:00am
IOCL centrifugal pumps and equipment arrived at gate and dispatched to lube oil jetty.
11:00am
Hiab truck arrived to lift IOCL pumps onto vessel.
2:10 pm- 5:21pm
IOCL Pumps arrived aboard Carib Valley.1 IOCL pump sited on Berth 6 and other pump sited on LMCS Barge.
8:00am
Paria continues to explore other pumping options inclusive of submersible sump pump.
8:30am
Paria explores option of subsea cutting of no. 36 sealine with IOCL.
5:00 pm
Two (2) Laing centrifugal vacuum assisted pumps identified and commenced mobilization
9:45am
LMCS Project Manager met with IMT and indicated there was a bar across the riser spool. Removal of hyperbaric chamber required in order to cut and remove the bar
11:31am
Paria informs and receives authorization from OSH Agency for removal of Hyperbaric Chamber.
8:45pm
LMCS Commenced removal of Hyperbaric chamber
7:30pm
8:00pm
7:30am
8:30am
9:30am
10:30am
11:30am
12:30pm
130pm
2:30pm
3:30pm
4:30pm
5:30pm
6:30pm
7:30pm
8:30pm
9:30pm
10:30pm
11:30pm
9:03pm
Coast Guard did not consider diving safe and inquired about alternate rescue plans
10.00am
Paria attempted to meet with the families at PAP staff club. However to facilitate the meeting, families had some requirements that Paria had to meet.
7:50 am
Lorena B to create ullage for receipt of oil from Berth 5
12:00pm
Lorena B berthed alongside Berth 5
12:00pm
Requested an operator to conduct a dip of the line
12.00pm - 1.06pm
Paria met and apprised the families at PAP staff club. Agreed communication protocols were set up. Families declined EAP support from Paria.
7.45pm
LMCS confirmed to Paria that they had informed the families of the incident.
4.30pm
Paria & LMCS met at the ICC & agreed to move efforts from rescue to recovery & to meet with & advise the families accordingly in person.
2.36pm - 4.00pm
Paria consulted internally to discuss status of ongoing rescue attempts & considered recovery options
5.30pm -6.30pm
Paria & LMCS visited the first family to inform of the move from rescue to recovery efforts. Due to response from family, LMCS's decision not to continue. Communication reverted to earlier agreed communication protocol
9:55am
Three Divers (Fyzal Kurban, Yusuf Henry and Rishi Nagessar) entered the water. Lighting and camera were installed.
8:00am
Toolbox meeting led by Mr. Victor Dhillpaul (LMCS HSE Officer) and Mr. Kazim Ali Jr on LMCS Barge
9:30am
Paria performed Atmospheric testing of the interior of the chamber via a 2.5" vent valve which was located on the top cover of the same chamber.
12:00 - 1:45pm
Carber plug testing crew arrived at Berth 6, performed checks. In consultation with Paria, confirmed that Carber plug testing to be waived due to out of roundness of pipe.
2:30pm
Paria operator observed a "T' tool being used.
1:38pm
Dive operation at No. 6 Berth suspended.
7:30am
Paria issues permits to LMCS to remove and install 50” flange, remove and install 30” riser pipe, remove 30”solid blank, conduct pressure test on flange weld, remove chamber and blank on top new riser
7:30am
8:30am
9:30am
10:30am
1:30pm
2:00pm
11:30am
12:00pm
12:30pm
10:00 - 10:30am (24th Feb)
Paria (Terrance Rampersadsingh) met LMCS (Kazim Ali Snr & Jr) at their OSSD site office to discuss resumption of work post unpermitted barge movement incident. LMCS 3 day lookahead discussed:-
Friday 25th, 2022: Remove old riser section from hyperbaric chamber, Install new riser section in hyperbaric chamber, Hydrotest installed flange on riser, Couple new riser section to riser flange and guarantee flange
Saturday 26th, 2022: Remove hyperbaric chamber from riser
Sunday 27th, 2022: Install top side piping and take measurements for installation of SO flange, Cut and install SO flange, Carry out inspection requirements
2:30pm (24th Feb)
Terrance Rampersadsingh spoke with Paria offshore maintenance team on the agreed works.
Approx 1030am Carber testing at Berth 5 in progress.
Toolbox talk done, JHA signed, Solid blank removed and awaited carber team's arrival, carber testing completed and departed to berth 6
7:30am
8:30am
9:30am
10:30am
11:30am
12:30pm
1:30pm
2:30pm
3:00pm
1:15pm (24th Feb)
Terrance Rampersadsingh spoke with Paria offshore operations team on the agreed works.
3:41am
Hyperbaric Chamber, Cable and Boom fell into sea. NO INJURIES REPORTED
2:04pm
Borescope Video footage provided to LMCS for a risk assessment for a dive operation by LMCS.
01:00am
07:00am
5.50pm
Oily water, diving gloves and a scuba tank followed by the bodies of the three divers in sequence (1st at 5.53pm) and then other diving equipment.
4:00am
10:00am
1:00pm
07:00pm
4:00pm
10:00pm
01:00am
07:00am
4:00am
10:00am
1:00pm
07:00pm
4:00pm
10:00pm
6.50pm
Water displacement operation was re-started however oil was seen emitting from riser and the pump speed was at its maximum with only 30psig on its discharge. Pumping operations were then aborted
01:00am
07:00am
4:00am
10:00am
1:00pm
07:00pm
4:00pm
10:00pm
9.30pm
Planning meeting held to discuss removal of oil from the pipe but the following constraints existed: Lorena B could only fit at Berth 5 due its size and that the Slops barge can take only 80 bbls at a time. ICT requested that a larger slops vessel (but smaller than the Lorena B) be sourced to use at Berth 6. The other option would be to discharge the oily salt water into 66 Sealine leading to potential integrity issues as well as having a commercial impact on crude loading. After a lengthy discussion, the team decided to pump from Berth 5 to the Lorena B.
9:00pm
Team performed a risk assessment and finalised operation procedure for a water displacement exercise using the inflatable plug that was already in the line.
1:00pm
Transfer of vacuum assisted pump to berth 5 completed
10:00am
Replacement crane barge (Seabass ) arrived.
9:00am-
LMCS Mr Ali and diving team arrived on site to discuss retrieval dive.
4:50pm
First phase of scaffold on berth 6 complete. Cutting of steel bar in progress
4:49pm
Decision made after consultations that a diver would not be sent into Berth 6 due to risk involved.
12pm
Risk assessment process on dive retrieval commenced
5.30am
Walkdown conducted to ensure that all site preparations were made at the risers on Berth 5 and Berth 6. Valve manifold and the scaffolding to access the riser at Berth 5 as well as the scaffolding at Berth 6 required adjustments. Liquid level on Berth 5 was lower than that was previously filled to and that the level at Berth 6 had risen.
7:30am
Team re-evaluated the risk assessment given the changed conditions of the 36 Sealine riser liquid levels overnight.
9.00am
Onsite Adjustments completed
10.45am
Vacuum assisted pump at Berth 5 started.
11.25am
Water emitting from Berth 6 riser.
11.48am
First hose connection failure
4.00pm
crawler was deployed and various objects and oil was seen. At around 5pm, at 700ft tether length, diving equipment was observed entangled.
7.00pm
crawler was deployed at Berth 5. Crawler went in to approximately 120ft before too much oil was seen on the bottom of the crawler tracks.
10.30pm
Planning meeting held to discuss a plan using the water displacement device from Berth 6 and discharging into the Lorena B as no other vessel was available to do the reverse and fit at Berth 6. This required the welding of a flange at Berth 6 riser, a valve manifold arrangement, a startup strainer. Arrangements were put in place for the fabrication / sourcing of material to occur during the night.
01:00am
07:00am
4:00am
10:00am
1:00pm
07:00pm
4:00pm
10:00pm
8.30am
Planning meeting held and Vessel Sea Manatee, having a nominal capacity of 1000bbls was confirmed to have been sourced. Arrangements made to have the Higher head multi speed vacuum assisted pump used at Berth 5 and higher volume multi speed vacuum assisted pump to take suction from Berth 6.
11.00pm
Vacuum Assisted Pump at Berth 5 started.
8.15am
Planning meeting on water displacement device
9.30am
NGC conducting site visit
5:53pm
1st Body Recovered
01:00am
4:00am
1:00pm
Team performed risk assessment for a water displacement exercise from Berth 5. In parallel, executed modifications to the suction strainer. The operations procedure was also updated to reflect the change of using 2 pumps during the water displacement device.
7.00pm
Sea Manatee arrived at Berth 6
1.45am
Pumping at Berth 5 was restarted to retrieve the water displacement device. Same was retrieved at 2am and the pump was shutdown.
0:39am
4th Body Recovered

## Feb 28 2022 (hidden)
TIME | ACTIONS
00:20hrs | Offshore OTS Beckles indicated to HSE Bachoo that skimmers will also be required and will liaise with HSE on | INVENTORY ISSUED FOR USE
| return from Berth#5 | 20 Absorbent Booms
01:01hrs | HSE Marcus Charles stated activity(scaffold modification) completed at Berth #6 and returning to Landing Stage. | 09 Containment Booms,
01:19hrs | HSE Marcus Charles stated operations preparing to fill line at Berth#5 with hydrant water | 30bags of Cansorb
01:20hrs | HSE Dillon stated pump is connected and operations will beign filling at 04:00hrs | 2 Disk Skimmers
01:29 hrs | HSE Richardson indicated Southern Pumping Services Ltd received 09 Containment Booms, 20 Absorbent Booms | 2 Power Pack
| and 30bags of Cansorb. All placed at Berth#8 | 4 Hydraulic Lines
01:56hrs | A. Khan from Mtce. Stated line is filled with Hydrant water and they will wait until 4am for further instructions | 2, 4" Suction
02:10hrs | HSE A Samuel; items delivered to berth #8 for Operations: 2 Power Pack/ 2, 3" Suction/ 2, 4" Suction/ | 2, 3" Suction
2 Disk Skimmers/ 4 Hydraulic Lines
02:32hrs | Scaffolders/ HSE Dillon and Charles back onshore
0536hrs | Final safety walk throughs being conducted on berths
0613hrs | S.Subero spoke to Nerissa about contacting SWRHA to source body bags
0614hrs | Update received from coast guard that they left staubles at 5am. Expected on site shortly.
0631hrs | Body bags located (4 present). Berth 6 water level in riser rose (8ft from the top) which is a change and re evaluation need to be done. Potential 9am start time.
0730hrs | Coast guard on site.
0750hrs | Review of the method and risk assessment with internal team and heritage to determine if any changes need to be made
0850hrs | S. Subero indicated that Marine security is located at Berth 6. One officer is on LMCS barge and one officer is on Berth 5. Coast guard is also assisting to secure the port.
0916hrs | M. Wei and team left incident center and headed to Berth 6.
0926hrs | Divers on standby in the event there is any blockage.
0942hrs | EAP personnel arrived to Incident command center and being set up in a room to be determined.
0953hrs | HSE Ramkissoon indicated that HHSL out on berth 6 with crawler for contingency- Gervais robley (team lead)
1011hrs | Coast guard L. Hargreaves (Commander) shown the video footage from berth 6 by security as per request
1014hrs | Coast guard and Osei (Heritage) requested that R. Archbald provide specs and photos of the two plugs used in the job.
1018hrs | Incident commander sought and received permission form General Manager to video events at berth #6. M. Wei contacted and advised that his phone will be used for the video. In the event that M. Wei's phone cannot be used Hassan Mohammed will utilise his phone.
1021hrs | P. Beharry indicated that final checks are being done on berth 6
1036hrs | M. Wei indicated that the Coast guard, security team, mechanical ppl and hse preparing to have a toolbox talk.
1038hrs | C. Piper indicated via telephone call to M. Wei that OTSL divers indicated that the pump specialist at No 5 Berth should be able to tell us if the bladder is moving and if we have flow, travel or squeeze. Pump specialist is Laing
1041hrs | C. Balkissoon indicated that Offshore 1 channel will be giving updates which may need to be deciphered to estimate flow, travel or squeeze. Virgil chattergoon indicated that they will Communicate pressures and flows.
1045hrs | C. Piper reported that the Pump started on berth 5. 700rpm and 10psi on the pump discharge.
1048hrs | Osei (Heritage) indicated that Heritage's Oil Spill vessel's ETA to Paria is 1130hrs
1100hrs | Heritage Oil Spill vessel Antique1 mile west of berth 6
1123hrs | HSE S. Ramkissoon indicated that a slow flow of water being seen on the riser at Berth #6
1134hrs | Offshore Channel 1 (OC1)- V. Chattergoon reported that they are Increasing pressure to 20psi
1140hrs | R. Archbald spoke to HHSL Anthony Viera regarding video raw footage. He advised that he will send link to R. Archbald. R. archbald spoke to A. Viera about his assistance to recover any objects at the base of berth 6 riser elbow. Requested HHSL to provide personnel and equipment to do confined space recovery. R. Archbald indicated that Viera advised that he will gather information and provide an update subsequently.
1140hrs | R. Nimlet instructed to increase pressure from 20psi to 25psi
1144hrs | R. Nimlet instructed to increase pressure slowly from 25psi to 40psi
1146hrs | HSE S. Ramkissoon indicated that pressure increased to 50psi
1147hrs | HSE S. Ramkissoon indicated to HSE coordinator no oil was seen coming from the riser at berth 6
1148hrs | HSE N. Charles indicated that there is a Leak on pump discharge at berth 5. Operations suspended at until further instructions
1156hrs | Osei (Heritage) indicated that Heritage Oil Spill vessel, the Antique is on site and situated 1 mile west of berth 6
1200hrs | HSE S. Ramkissoon reported to HSE Coordinator that all Operations paused as there is unauthorized access in the area. Drone flying over the riser at berth 6.
1207hrs | HSE S. Ramkissoon reported to HSE Coordinator that drone has left berth 6 and heading to the direction of flower pot.
1213hrs | HSE S. Ramkissoon reported that operations resumed
1214hrs | HSE N. Charles reported Operations halted once more. Discharge line defective. Hose burst.
1219hrs | HSE S. Ramkissoon reported of a minor injury on berth 5. A launch is coming to take the person back. No further information at this point
1224hrs | HSE N Charles reported that minor injury involved chin bone coming into contact with table after being startled after hose ruptured.
1224hrs | HSE S. Ramkissoon (SR) indicated that the Crawler is being deployed at the riser at berth no 6.
1232hrs | HSE S. Ramkissoon (SR) 40 persons on the berth 6 and 32 people on berth 5 including LMCS and excluding Cudjoe.
1236hrs | C. Piper requested a breakdown of persons on site and asked whether 3 HSE persons are required on site. HSE Coordinator indicated those person present for Rigging support for Coast Guard. R. Archbald indicated that we will act on the situation and ask M. Wei to figure out who is need for operations and time needed for each operation. R. Archbald to liaise with M. Wei. Prakash Beharry to help facilitate.
1241hrs | R. Archbald advised that before the crawler is deployed it should be Ensured that RA covers the change with the pressure that the crawler will encounter.
1244hrs | HSE S. Ramkissoon (SR) indicated that the Crawler was deployed.
1317hrs | HSE S. Ramkissoon indicated crawler was introduced @74ft one rope was found @98 feet one scuba tank was found. Crawler was taken out.
1322hrs | HSE S. Ramkissoon indicated that the crawler was removed and pump will be restarted to see if there will be any movement of the objects found
1323hrs | S. Chadee from the Ministry of Energy arrived at the Incident command Center
1350hrs | HSE S. Ramkissoon indicated that the hose has not yet arrived at Berth 5
1420hrs | HSE S. Ramkissoon informed that Pumping operations resumed at 30psi
1422hrs | HSE Coordinator advised S. Ramkissoon to look out for any oil
1428hrs | Offshore Channel 1 (OC1)-V. Chattergoon reported that they are Increasing pressure to 70psi
1429 hrs | Offshore Channel 1 (OC1)- R. Nimlet indicated that they increase pressure to 90psi. V Chattergoon indicated a hose coupling came off. Operations paused.
1455hrs | HSE S. Ramkissoon indicated the crawler is going to be deployed at berth 6.
1526hrs | HSE Coordinator indicated that OSH verbally requested footage from Paria. OSH to send written notification requesting same. OSH inspectors informed they will be visiting tomorrow (01/03/22)
1546hrs | HSE N. Charles indicated that a elbow was installed on the riser on berth 5. Coupling of the hose still to be done.
1554hrs | HSE S. Ramkissoon indicated that the crawler came out of the line
1602hrs | C.Piper requested if we can get any of the crawler footage taken today. To be confirmed.
1606hrs | C. Piper requesting while pushing if the crawler can remain inside a few feet away to observe movement
1608hrs | M. Wei indicated that Tubing may be able to pull any object out (1/2 inch or 1/4 inch). Continue to push but monitoring how much water can be pumped out before oil affects visibility. M. Wei indicated that we observed a 23 feet movement of object towards berth 6 from crawler data. M Wei. indicated that Brainstorming would be the best to determine way forward.R. Archbald advised that we determine the best hook type for the job to be conducted. Coast Guard to assist.
1634hrs | HSE Coordinator indicated that a tripod and rope will be sent out to S. Ramkissoon in the event additional equipment is needed.
1638hrs | IC spoke to Mr. Kazim Ali and he (Mr. Ali)suggested the following be added to the equipment listing: 3 Scuba tanks with harness and facemasks, 12" long flogging spanner, ring spanner, knots and bolts
1648hrs | Offshore Channel 1 (OC1)-Crane barge arrived to Berth 5 with the hose.
1715hrs | HSE S. Ramkissoon indicated that the crawler is being re-deployed at Berth 6
1733hrs | P. Beharry indicated that hose is being installed currently on Berth 5
1742hrs | Offshore Channel 1 (OC1)- V. Chattergoon reported that they are testing the pump before resuming operations
1745hrs | Offshore Channel 1 (OC1)- V. Chattergoon indicated that pumping is resuming at just below 50psi
1746hrs | HSE conducting risk assessment and Technical creating method statement for the tubing and hook
1749hrs | HSE reported one of the cylinders has surfaced
1750hrs | Offshore Channel 1 (OC1)- Oily water surfacing
1751hrs | Offshore Channel 1 (OC1)- Pump rpm 1675. Pressure gauge not functioning efficiently
1753hrs | HSE reported- First body surfaced
1754hrs | HSE reported- Two additional bodies surfaced
1754hrs | TTPS formally notified by S. Subero
1756hrs | Hse coordinator notified S Subero
1757hrs | Offshore Channel 1 (OC1)-V. Chattergoon indicated they are currently clearing the riser
1758hrs | Steve Lalbeharry of the Environmental Management Authority informed of spill around berth 6 by R. Archbald
1758hrs | HSE reported- Slight sheen around berth-Majority of oil in containtment (est 1/4 barrel)
1800hrs | Offshore Channel 1 (OC1)-R. Nimlet indicated to shut off pump as persons are heading to riser area. Coast guard assisting.
1758hhrs | S.Chadee of the MEEI was formally notified for spill around berth 6 while on location at the incident command room by R. Archbald
1801hrs | Shevon Ali Chief Inspector OSH agency formally notified of the recovery of three bodies surfacing at no 6 berth and that they are being retrieved by the coast guard at this time. Informed of slight sheen which is being dispersed mechanically
1810hrs | S. Ramkissoon indicated that a light Sheen 350 ft width Westerly direction being seen
1811hrs | Gull notified and hiding out and Cudjoe Pirogue also heading in that direction
1816hrs | IC indicated TTPS on site heading to landing stage
1821hrs | Hse coordinater requested all HSE technicians on land to head to landing stage with appropriate ppe including disposal coveralls and other equipment necessary for handling bodies
1824hrs | Hse coordinater requested all HSE technicians be respectful of the bodies and carefully perform their duties
1837hrs | S Ramkissoon reported that M. Wei requested sanitization agents for (soaps, machine, sanitizers) at the incident location and the launch (area where bodies are traversing)
1843hrs | Offshore Channel 1 (OC1)- Additional sorbent booms being used
1847hrs | S Ramkissoon additional body bags are required. Ones that are present are bursting.Request the body bags at the launch landing
1848hrs | Offshore Channel 1 (OC1)-R. nimlet indicated to ramp up pump quickly once started
1850hrs | Offshore Channel 1 (OC1)-R. nimlet indicated20 psi. Open up qucikly to 75 % . Oily water surfacing
1852hrs | HSEQ Lead informed all HSE personnel all permits are valid no renewals required. Inform maintenane and operations personnel
1853hrs | Offshore Channel 1 (OC1)-R. nimlet indicated pressure not rising above 30psi. Stepping up rpm and observing
1854hrs | Offshore Channel 1 (OC1)- Oil surfacing.Nimlet instructed V. Chattergoon to Shut down and close off.
1857hrs | HSE coordinator notified by S. Ramkissoon that because of poor lighting it is undertimined if oil breached the containment barrier
1859hrs | A pirogue was sent west of berth 6 to mechanically disperse if any oil is seen on water
1903hrs | HSE Coordinator reported that Launch landing now closed to vessel movement
1909hrs | Offshore Channel 1 (OC1)- no more pumping operations for the night
1915hrs | R. Archbald indicated that M. Wei reported that operations will continue. There was a pause to confirm with Kazim Ali that there were bodies to retrieve. Confirmation received. 4 bodies to retrieve | Joel Smart- Laing Anton Noel- Inland jetty
1924hrs | Wahoo left berth 6 with six persons to landing stage
1932hrs | Wahoo has arrived at the landing stage
1936hrs | ICP Called Offshore Channel 1 (OC1)- Asked for confirmation on pumping operations. R. Nimlet confirmed no pumping operations for the rest of the night from Berth 5 to 6
1950hrs | Stephenson Thomas from MEEI was introduced to all persons in Incident command room and releived S.Chadee
1951hrs | Sandiford HSE retrieved three of the bodies at launch landing. Sending body bag back to Berth 6.
1957hrs | M.Wei requested harnesses and lanyards (Approximately three)
2007hrs | At 1815hrs anton noel was found using his cell phone and was escorted out as per guidelines
2013hrs | S. Ramkissoon indicated that Personnel are fishing a line into the hole with a hook in hope of retrieving the fourth body
2018hrs | Gloves,tape, paper towels and jumbo garbage bags requested by Chad (HSE) at the Landing stage location.
2022hrs | Chad (HSE) requested that HSE Lead be informed that all activities are on standby
2028hrs | S. Ramkissoon indicated that there is no visual of the fourth body as yet. They are currently probing the line at approximately 100 feet. Pumping was stopped due to large volumes of hydrocarbons at berth 6
2038hrs | S. Ramkissoon indicated that probe was deployed at 100 feet and found nothing thusfar and are pulling out. Management team heading back.
2045hrs | S. Ramkissoon All personnel leaving berth 6. HSE Coordinator requested that sorbent booms be clipped onto the riser. S. Ramkissoon indicated that the top of the scaffold is covered in oil. HSE Coordinator requested that a dynamic risk assessment be conducted to carry out placement of the booms in a safe manner.
2050hrs | S. Ramkissoon indicated. All sorbent booms was utilised in the water. S. Ramkissoon indicated that the last report by Catherine indicated that Riser seems to have approximately 100 barrels of hydrocarbons. Operations to return to discuss with ICT the best method of removal.
21:07hrs | HSE Coordinator to Chad Ramkissoon, we are wrapping up operations at this time
21:08hrs | HSE Lead- outlined LMCS work on Berth #6 Riser and incident that took place to the Ministry of Energy Official:
Stephenson Thomas.
21:16hrs | Mtce Personnel awaiting approval to board launch. Offshore OTS, TTDF is in control of Landing Stage and has
locked down area. No external movement permitted
21:24hrs | Vincent Heeralal- inquired from Osei if Heritage has any slops barge available. Osei indicated negative
21:25hrs | M. Wei, we are not standing down tonight, Best option is to empty from Berth #6. Slops Barge needed and a pump
21:26hrs | Ministry of Energy official Stephenson Thomas identified himself
Osei asked if pumping Berth #6 is best option, M. Wei stated yes.
21:27hrs | GM Mohammed: what is the decision made? M. Wei: water too oily to flush, pumping will throw oil into the sea
A bigger slops barge is needed, current capacity is too small. Need to move 1200bbls
Catherine: pumping into 66SL as an option, but not advised because of too much erosion of line
GM inquired on how many people are needed. M. Wei indicated 5-6 tonight. GM stated we cannot say we are
stopping operations. We are reassessing to options available but must not stop.
21:29hrs | M. Wei:best option available is to get a vessel to collect 1200bbls. GM: will using a power pump destroy the body?
21:34hrs | GM stated the team needs to get the vessel. M. Wei indicated commercial will be the best to source, but it can take
up to a week. GM reiterated we cannot stop or shut down tonight. Instructions to team to get a solution, find the
equipment and it must be a humane process
21:36hrs | Rene Nimblett: we must pull from Berth#6. Pulling from Berth #5 will move the body backwards towards Berth#5.
Currently the fluid is an emulsion. Osei asked what is the volume for continuous pumping? Rene stated he is unsure
because of the visibility. At the time, fluid was approx. 70/30 water to oil. Pumping was stopped because oil volume
started to increase.
21:38hrs | M.Wei: let us stop, think and find a solution. C.Piper suggested allow the oil to settle and pump to slops barge.
21:40hrs | Anthony Sylester asked: Can we stop and indicate we made progress?
C. Piper: we have instructions from the GM not to stop any operations. We are unable to get a vessel on such
short notice. GM reiterated that we must not stop even if we have to take a bit of time to regroup
21:42hrs | A. Sylvester: Is everyone in agreement with suspension?
C.Piper: we are not suspending operations, we are brainstorming to find options and a solution
21:44hrs | V. Chattergoon: the original plan was to pump into Lorena B. Is this still possible? We can pump into Lorena b at a
controlled rate, then send in the crawler. Readings showed the pressure was up to 50psi then dropped to 20psi
Mr. Piper: is the bladder on Barrier damaged on Berth #6. V. Chattergoon indicated yes.
Mr. Piper: the Lorena B will be placed at Berth#5 tonight. We will be pulling from berth#5. V. Chattergoon: Is there
potential for damage to the body? Piper: possible but not sure.
Offshore OTS beckles indicated that oil is closer to Berth#6. Catherine advised that pumping from Berth #6 to#5 can
cause the barrier to become wedged again. Mr. Piper: with the Lorena B at Berth# 5, we can repeat operations to
fill and empty.
22:05hrs | GENERAL CONSESUS IS TO USE LORENA TO COLLECT OIL FROM BERTH!
C. Piper informed TTCG that they could stand down for tonight. Coast Guard indicated they do not want a repeat of
short notice and hiccups. C Piper stated they will give sufficient ntoice tomorrow.
OTS Beckles also advised that a crew change is needed at this time
22:06hrs | Rene Nimblett: flushing and pulling must be done the same way each time. The scuba tanks obstructed before, but
they are removed now.
C. Piper issued a directive to OTS Ramdhan and Beckles to arrange the pilot vessels for the Lorena B to be at Berth #5
22:25hrs | Prakash trying to source a Barge with capacity for1200bbls. C Piper advised this is not necessary. The Lorena B has
available space for 9000bbls.
22:35hrs | C.Piper to Randy: the body is in water and we're not sure why it hasn't surfaced. Reports are while pumping from Berth
5 to 6, 70psi was attained, however this dropped to 30psi despite operator increasing pump RPM. Possible that the
bladder on the barrier was passing and Oil Water was observed. Current option is to place Lorena B at Berth#5 and
suck out riser.
22:38hrs | Randy asked C. Piper what does empty mean?Is it the lowest the hose can go?and how deep is that?
C. Piper stated 60ft but isn't sure the hose will pass the elbow. Randy: then we might be able to get 800bbls. Are we filling
first or filling and suctioning at the same time. What are the potential problems?
C. Piper: a hose can burst, loss of suction/no suction. Randy: Can the last package get stuck onto the suction hose?
C. Piper: it is possible. The hose is 8" and Pipe is 30", there is little suction force. The aim is to remove the oil.
22:42hrs | Randy updated Osei and Paul on discussion with C. Piper
22:43hrs | C. Piper: the crawler can go in as far as 600ft to locate last body or observe any obstructions.
22:45hrs | Randy: Did the plug help the bodies to surface? C. Piper: yes and the plan is with better visibility, we can see any
obstructions and devise a plan of action to retrieve the body.
Randy asked if a Dip is possible to get the oil height. Beckles stated the hoses need to get lifted to the berth. C Piper
advised Beckles to use the Sea Bass.
Terrence stated we have no documents. Randy advised that Akil and the HSE Team will assist.
Beckles indicated sanitisation of Landing Stage is needed. Randy advised HSE Team will assist as well, sanitisation must
be done. C. Piper advised to shut down the Wahoo and use the other vessels
23:00hrs | Terrence expressed reservations about starting a new job at night and what is the goal of this job?
23:03hrs | Randy replied to remove as much oil as possible. C. Piper: a dip has to be done at Berths 5 and 6
23:05hrs | Randy inquired if more containment booms are needed. Beckles stated we have mobilised that from last night.
23:07hrs | Randy also advised that we need to identify contractor employees who require a rest due to long hours
23:15hrs | HSE advised that an undetermined foul scent at Landing Stage detected
23:20hrs | Catherine discussing the flushing and pumping procedures, use of crawlers and options. The possible effects on the
body.

## March 01 2022 (hidden)
TIME | ACTIONS
00:10hrs | OTS Ramdhan requesting sanitisation of vessels and Landing Stage, No water available. Akil Samuel to contact
TTFS for assistance.
00:33hrs | TTFS arrived onsite at shipping heading to Landing Stage.
00:35hrs | HSE Charles advised by HSE Bachoo to liaise with TTFS to provide disposable suits to TTFS involved in washing areas
00:39hrs | SOC requested by HSE Bachoo to advise TTFS to hold on activity until HSE Charles liaises with them
01:08hrs | TTFS departed Paria Facility after assisting with cleanup
04:00hrs | Lorena B in place alongside Berth#5 to facilitate pumping activity
Site set up and area mobilised at Berth#5
04:15hrs | Laing demobilised pump at Berth #5
0615hrs | Dunstan Delpino of MEEI relieved Stephenson Thomas at 0600hrs
06:15hrs | HSE Coordinator requesting shipping to conduct pollution check west Berth 6 and west as far as anchorage and warf
0650hrs | Offshore Channel 2 (OC2)- Kingfish reported that crude is flowing slightly over boom at Berth 6. Sheen heading in a SW direction.
0652hrs | OC2- Kingfish reported that the integrity of the containment boom is not compromised at this time
0720hrs | P. Beharry indicated that the forward plan is to pump from berth 5 and clear up the line to send in a ROV. IOCL pump to be used on berth 5. Setting up to pump from Berth 5 to Lorena B. Permits currently being written. Laing pump being moved from Carib Valley to Lube Oil Jetty. IOCL pump on barge going to carib valley. Concurrently organinsing to make arrangements to pump seawater into Berth 6 in a controlled manner to clear up the line. HSE reported a slight sheen SW of berth. Cudjoe urgently dispatching a pirogue.
0820hrs | Akil Samuel HSE in route to berth 6 conducting pollution checks
0849hrs | Akil Samuel HSE reported southern part off berth #6 contained within boom. Sheen leaving berth heading westerly. Sheen being seen in the vicinity of berth 7. No resources deployed as of it.HSE coordinator inquired as to what Resources are required for berth.Nothing has left our anchorage based on our survey this morning. Using a gauging tape it was estimated that the thickness is 5mm. Estimated area of sheen 50 to 60 sq meters. Resources to be determined post hse survey.
0915hrs | HSE Coordinator indicated that the plan is to source a slop barge to collect the oil contained in the boom and deploy skimmers and assess if further resources required.
0928hrs | HSE Coordinator requested that oil spill supplies (Absorbent booms and garbage bags) be deployed to berth 6.
0943hrs | HSE Coordinator spoke to Lt. Hargreaves
0952hrs | NGC on site to have a pre meeting before a site visit at berth 5 and berth 6 prior to possible pigging of the line using either 2lb or 5lb pig .A. Sylvester explained the process that was conducted thusfar. There are two laing pumps available a high head pump and the pump utilised yesterday on berth 5. Potential plan is to use the existing pump and have the high head pump on standby. Shamael Ali of Heritage indicated that Heritage process engineers can sit with Catherine and her team to develop method and risk assessment.
1000hrs | V. Heeralal indicated that the existing crane barge may need to be changed out, however, that seems to be an issue as all permits would then be obsolete. Existing crane barge has another job
1019hrs | No visible presence of sheen/slick/oil observed in a easterly direction. Presently current is travelling in a westerly direction. Skimmers, absorbent and cansorb to be used on the oil contained in the boom to ensure it doesn’t breach containment
1022hrs | HSE Coordinator spoke to Dion Lawrence of the OSH Agency and updated him on the recovery operation and indicated that we are currently exploring options and no pumping is taking place at this time. OSH to visit Incident command center at 1130 am where they will be appraised of process thusfar and will request any documents etc. formally at that time.
1045hrs | C. Piper informed S. Subero to facilitate retrieval of the go pro (In lmcs possession) with the police
1056hrs | V. Heeralal indicated that the Seabass barge will be changed out. Documents for the new barge to be received to ensure lift plan and permits are in place. Potential changeout @1300hrs
1107hrs | S. Deyalsingh of Heritage arrived to the incident command center with a team to aid with potential oil spill response efforts. He indicated he would have a conversation with M. Rudder and have him on standby.
1114hrs | HSE N.Smart indicated that he activated the hot work permit on berth 6 in preparation for the HHSL crawler to go back in the pipe.
1145hrs | Heritage and NGC completed site visit and returning to ICP to discuss forward
1227hrs | S. Ali of Heritage indicated Inpection of berths 5 and 6 completed. From the site visit it was noted that the pig would be launched frm berth 5. It would be Installed in line bolt flange and start pump. 2lb and 5lb density pigs. 2lb will be used first. No additional ra should be be needed as covered under pumping operations. To install pig in line same ra could be used. NGC on standby . 20 mins ETA once a go ahead is given.
1234hrs | HSE Coordinator requested that HSE personnel check and ensure the Wahoo is adequately sanitised. Skimmer equipment being loaded on the vessel
1327hrs
1342hrs | Kerry Rampersad (Onshore Lead- Heritage) arrived at ICP
1340hrs | OSH Arrived at adminsitration building to be appraised of the incident and progress thus far. OSH representatives include Rishi Roopchan, Trevor Mohan, Fiona Mcdonald and Jason Lookhoor. | To fill in when the meeting started
1359hrs | HSE -Sandiford 1 containment boom and one absorbent boom is currently at berth 6. Skimmer not yet on site
1421hrs | HSE -Kwesi reported that operations are currently removing oil from the riser via bucker and placing into barge
1422hrs | HSE Coordinator indicated that the coast guard in Point A Pierre anchorage being transported at No 6. berth
1518hrs | HSE- Kwesi indicated that they took probe into the rise and no oil in pipe. Crawler will be sent into berth 6 in 5 mins.
1532hrs | HSE reported that skimming operations have begun at Berth 6
1604hrs | Heritage vessel arrived with oil spill supplies. Shyam Dyal notified.
1605hrs | Crawler log: V. Harrichan relayed real time crawler footage information to ICT starting at 240 ft
1614hrs | Crawler at 315 ft oil spotted 6 inches thick running for around 3 feet
1619hrs | Crawler at 320ft
1620hrs | Crawler at 327ft- film of oil decreasing in thickness
1621hrs | Crawler at 334ft
1622hrs | Crawler at 340ft
1623hrs | Crawler at 348ft
1623hrs | Crawler at 350 ft
1624hrs | Crawler at 360ft
1624hrs | Crawler at 362ft
1625hrs | Crawler at 380ft
1626hrs | Crawler at 389ft- pocket of oil 6-8 inches thick
1628hrs | Crawler at 410ft- pocket of oil getting thicker. Approx 10inches .
1629hrs | Crawler at 430ft
1630hrs | Crawler at 435ft- thick layer of oil >10 inches
1631hrs | Crawler at 448ft- thick layer of oil Approx 10 inches.
1632hrs | Crawler at 450ft- Radio seen floating
1638hrs | Crawler at 460 ft- Crawler slipping at the bottom of the pipe. No traction.
1639hrs | Crawler at 473ft- Layer of oil still being seen
1641hrs | Crawler at 488 ft- Not much tether to go forward. Using electrical cable to get closer to platform (Additional 150ft)
1643hrs | Crawler at 540ft- Still observing oil. Thicker oil (Approx 6 inches)
1645hrs | Crawler at 540ft
1647hrs | Crawler at 567ft- Piece of steel plate on floor (8inches x 10 inches)
1649hrs | Crawler at 573ft- Passed steel plate
1650hrs | Crawler at 595ft
1651hrs | Crawler at 600ft
1651hrs | Crawler at 616ft- 10 to 15 feet of traversing capability left
1654hrs | 120ft additional received when the extension is rec'd
1655hrs | Crawler at 698ft- Object seen tangled with rope
1657hrs | Crawler at 698ft- Object looks like a deflated bag. Instruction from ICT to pause. M.Wei and C. Balkissoon indicated that they would head to site
1738hrs | HSE- Kwesi indicated that coast guard is requesting permission to do a dive on the sea floor around the berths
1750hrs | Rointra Hosein of the MEEI relieved Dunstan Delpino at the ICP
1754hrs | HSE Coordinator indicated that IMT has given approval to dive
1810hrs | S.Subero indicated that Coast Guard divers did a dive and conducted checks under piles of berth 6. Nothing seen.
1822hrs | HSE issued 4 pelican 3315 flashlights to operations
1855hrs | HSE Kwesi- Skimming complete and crawling complete on Berth 6
1856hrs | R. Archbald indicated Method statement and JHA completed for pigging operations
1902hrs | HSE indicated All equipment is now on berth 5. Crawler to be sent in prior to pigging operations
1926hrs | HSE indicated that Crawler deployed at Berth 5
1931hrs | Crawler log (Starting at 90ft):
1931hrs | Crawler at 90ft
1933hrs | Crawler at 110 ft- Nothing notable seen
1937hrs | Crawler at 166ft- Slick of oil seen. Trying to locate well seams
1938hrs | Crawler at 167ft- Film of oil 12 inches ( camera was unable to look up). Technician only willing to go 250ft seeing oil at wheels of crawler.
1940hrs | Crawler at 170ft- Top of oil closer to camera. Technicians are backing out as the resistance of the tether may stick. Thickness of oil holding back the tether. Damage could be done to the machine
1946hrs | Crawler backing out ar 162ft- Oil still at top of camera 12 inches thick
1946hrs | Crawler backing out ar 150ft- Oil still at top of camera 12 inches thick
1947hrs | R.Archbald calculated that approx 200 bbls in pipeline
2005hrs | R. Archbald advised pig can get moving. Observe until see oil, pause and decant if we have something to decant into
2006hrs | C. Piper indicated that the first 10 barrels may have to flow into the environment (All booms and monitoring vessels will be in place)
2010hrs | S. Dyal indicated that there are two potential scenarios according to the trajectory. Cedros/Venezuela or La Brea with undercurrents He indicated that his team will be working all night to get the forklift to load and deploy the boom Vikomas skimmers can be used but there are no containers to put it in. If empty totes can be provided can pump it in. 4 totes of dispersant on vessel Vessels need to be deployed in the morning to break up sheens 2 drones will be deployed at 4am 1 offshore and 1 at the shoreline
2102hrs | Meeting Updates #3- with Heritage Petroleum
meeting information contained in word document
22:00hrs | All agreed to end meeting to give stakeholders time to discuss options and develop solution.
22:09hrs | C. Piper: Tough Situation. If not done properly- we may end up with 3 months of an environment issue fighting an
oil spill
Catherine:~200bbls to be pumped and S Dyal indicated we can safely handle 20-50 bbls
GM: If we choose a slower option, how do we proceed. Catherine: Slow and Steady Decan twill get the oil out, but
its a long process.
GM: If we push one more time, what's our options? Catherine: we can pump into 66SL, but the risk is high, line might
22:12hrs | leak. Rene: It might end up in next shipment. Randy: how will it go into 66SL? Catherine: use a flange to connect
C. Piper: From riser to flange what hose do we need? GM: Can we pump from 36SL to 66SL easily? Rene: Yes
GM: next shipment is on 05thMarch, so we can flush easily. Saltwater will stay in the line for only 2 days. Then we pig
Rene: we can do the reverse process: B#6 to B35 to Lorena B. Catherine: It is a fast proces, but there is the issue of
obstruction in the line.
22:30hrs | General Consensus : it is easier to pump from B#6 to B35 to Lorena B
22:32hrs | M. Wei: We can set up and be ready to pump by 4-5pm tomorrow afternoon.
GM: Pigging can be done after. Rene: Aim is to collect solids, move catchment from B#6 to B#5. Crawler use is not an
option. We want to pump oil and pig after. Should be a 24hour solution.
Randy will talk to OSH to get ok for work to be done on B#6
GM: Can all procedures get us ready for 4-5pm tomorrow? Catherine& M Wei.: mostlikely
Catherine: this option prevents the environment problems.
Beckles: We would need about 3-4 lengths of hoses.
23:00hrs | M.Wei: discussin current status of B#6and B#5 and what is needed. D Jaglal Contractors to be contacted and put on
notice for works tomorrow.Prepare site and be ready for works.
Work process was discussed with Terrence.

## March 02 2022 (hidden)
TIME | ACTIONS
0600hrs | Isaac Furlonge of the MEEI arrived at the Incident Command Post
0800hrs | Heritage support team (Dion callendar, serpentarium) proceeded to the HSE office
0811hrs | IMT meeting with Heritage commenced to decide on actions for this morning
0841hrs | IMT meeting with Heritage to decide on actions for this morning
0857hrs | C. Balkissoon indicated that the decision on whether we are getting a barge or not is critical
0859hrs | P. Beharry indicated he was not comfortable with the operation and asked to be excused
0910hrs | HSE A. Samuel indicated that pollution surveillance was conducted around berth 5 and berth 6. The vessel travelled 2nm West of berth 6 and no sheen was seen. After Skimming operations yesterday, it is observed that 15sq meters of oil is still contained in the containment boom. There is also a slight sheen apprx 300m around the containment. There are pockets of isolated oil which cansorb can be used on located between the absorbent boom and containment boom
0949hrs | S. Ali of Heritage indicated to M. Diptee that the Frac tank option not feasible at this time. Pushing forward with the barge option (Seamanatee)
1040hrs | S. Lalbeharry of Ema informed by R. Archbald of the plan thusfar. He requested we deploy the drones before the operations commence.
1047hrs | M. Diptee indicated that the Seamanatee is three hours out
1147hrs | Offshore business given instruction to release the manatee.Utility vessel to release sea manatee from its moorings. Estimated time to depart 1-130pm.ETA to paria in three to four hours
1205hrs | C. Balkissoon working a backup storage plan with possible use of frac tanks.
1232hrs | Staff Meeting with Paria employees ETA 1300hrs
1244hrs | Sheldon Subero to give body bags to Coast Guard.
1245hrs | HSE to assit and travel with coast guard with body to sure.
1323hrs | 4 LMCS Employees on the sunny day to "man" vessel. No work was authorised to be conducted.
1327hrs | OSH requested through R. Archbald to visit the site today. Will advise at what time they will arrvie.
1410hrs | OSH arrived on site and are being briefed (HSE Briefing). heading out on a site visit to Berth 6
1418hrs | HSE Coordinator indicated HSE has received 6 body bags
1441hrs | HSE A. Samuel indicated that two members of the OSH authority left the landing stage to head to berth 6 for a site visit
1553hrs | W. Boodram updated that NGC arrived at administration gate and also updated that the Sea Manatee is expected to arrive at approximately 17:30hrs
1654hrs | OSH departed berth 6
1656hrs | M. Diptee indicated that the Seamanatee ( is delayed and arrival is expected at 1900hrs and frac tanks are en route (2-500bbl)
1729hrs | HSE M. Charles indicated minor streaks of oil outside of containment boom. This was a result of the sea dolphin agitating the water. Cansorb to be utilised. Containment boom integrity still sound
1839hrs | S. Dyal indicated that the Seamanatee if ten to 15 mins away from site
1948hrs | C. Balkissoon indicated that the pumping will start in approximately one hour (2049hrs)
19:56hrs | M. Diptee indicated the Sea Manatee arrived at Berth 6 at 19:00hrs.
20:30hrs | R. Nimblett: Pid is installed on Berth#5
A. Phillip: Barge is here. just about to bring it alongside Berth
20:38hrs | HSE M. Charles: Sea Manatee in process of being Berthed
21:17hrs | Sheldon Subero advised security to condcut patrol at Berth#1. Reported sighting of a pirogue
21:40hrs | HSE Smart: Berth#6 Sea Dolphin line up in progress
21:41hrs | HSE Hills: Berth #5 Hose connection to riser underway
21:54hrs | HSE Hills: Berth#5 completed and ready to proceed
HSE Smart: Berth #6 incomplete. Will advise when preparations are completed
22:00hrs | R. Nimblett: approximately 20 mins for all connections to be completed and ready.
22:16hrs | Rene: final stages of connection, Next contact will be to start pumps.
22:19hrs | HSE Smart: All connection are completed. Pump is ready to start
22:23hrs | Rene: radio check to Vergil, Arian. All loud and clear
22:34hrs | Arian: toolbox talk about to be conducted on the Manatee
22:47hrs | Arian: Sea Manatee ready to proceed. Max Capacity is 868 bbls across 2 tanks. Max Flow rate is 1000 bbls/hr.
Rene: Est. 1200bbls. Intention is to allow clean water into sea and when dirty water starts, it goes into tank. We should be below 868bbls
22:50hrs | HSE Hills: B#5 ready to commence.
Vergil: V1: 100% opem, V2:100% closed, line operator: Joseph
22:53hrs | Rene: OK to commence
22:54hrs | Vergil: Pump started and idling at 700rpm. no effluent observed
22:57hrs | Rene: any movement on vaccum gauge? Vergil: No vaccum gauge on line
23:04hrs | Vergil: Pump cycled, no leaks and suction hose will be pulled up to inspect for any issues
23:08hrs | Vergil: Flow is on 4" line/ going to conduct a few more checks. Rene: we are ready for when you open Vi
23:12hrs | Rene: Laing operators confirmed that Berth 5 can commence
23:13hrs | Virgil: Pressure guage reading nil. 700 rpm. Flow through V1.
23:15hrs | Virgil:Opening up slowly on V2
23:16hrs | Virgil: 50% on V2. Nil psi
23:18hrs | Rene: Open V2 and Start to Close V1
23:20hrs | Rene: Movement being seen.
23:20hrs | Virgil: Pressure still zero
23:21hrs | Rene: Water slowly emerging from riser. Priming pump on Berth 6
23.22hrs | Virgil: V1 60% closed, 40 % open.
23:23hrs | Receiving on the Manatee
23:24hrs | Virgil: Pressure still zero. Heading to fully closed on V1
23:25hrs | Rene: Clear water being seen at riser. will continue with same.
23:26hrs | Virgil: RPM 700 Idle speed: 700
23:26hrs | Rene: Remaining with same. Virgil: Still zero on pressure.
23:35hrs | Rene: any change in pressure? Vergil: still zero. Rene: Clear water on this side (Berth#6)
23:39hrs | Rene: still clear water, no change in pressure.
23:48hrs | Vergil: currently~2-300 bbls per hour. Pressure still zero
23:59hrs | Ministry of Energy Official Shazil Yasir arrived to take up duties

## March 03 2022 (hidden)
TIME | ACTIONS
00:07hrs | Rene: any update. Vergil: Negative
00:15hrs | Reports of Drone sightings at Berth#5 and Berth#6
00:24hrs | Rene to Vergil: started to get oil, Berth#6 staring pumps
00:26hrs | Rene: Shut down, something observed.
00:32hrs | Rene: Vergil open V1 to 25%. Vergil: opened to 25%
00:33hrs | Rene: Go to 30%. Vergil: 30% and holding
00:36hrs | Rene asking Arian for FLow Rate.
00:38hrs | Rene: Standy By Something is coming up shortly
00:39hrs | Rene: shut down, body sighted and retrieval to be attempted
Vergil: Pumping operations stopped at 00:39hrs at Berth#5
00:40hrs | HSE Smart to HSE Coordinator: Body sighted at 00:39hrs.
00:56hrs | Rene:There may be a small change for where they may pick up the body
Circa (Hassan) Body retrieved and other objects. Objects were photographed by C. Balkissoon and remained on the berth because of it's excessivly oily nature.
01:17hrs | HSE Smart to HSE Coordinator: Body loaded onto Wahoo and proceeding to Landing Stage. HSE N Charles advised of situation.
01:20hrs | HSE N. Charles indicated that the diver's tank, headlight and the pig were discovered inside the riser
01:33hrs | Offshore OTS Beckles informs Wahoo they are to proceed to shore
01:36hrs | HSE Smart requesting additional disposable coveralls, degreaser for clean up operations
01:42hrs | HSE Hills: pumping restarted at Berth#5
01:45hrs | Wahoo arrived at Landing Stage with Body
01:51hrs | HSE Coordinator to HSE Smart: please retrieve any other items that came up
01:54hrs | Body loaded onto Landing Stage
01:54hrs | DMO Arrival with Undertakers
01:58hrs | Rene to Vergil: Shut Down Pumps, Water Displacement Tool retrieved
02:07hrs | Undertakers, Police removed body from Paria facility. Undertakers in vehicle TDZ6050
03:40hrs | HSE and Maintenance Personnel arrived at Landing Stage
0853hrs | S.Dyal: Objectives- Drone surveys as per trajectory, to Point Lisas and as far as La Brea (North and South) Dion Callender is leading drone operations. Andy Williams is lead for clean up operations. Awaiting oil to be removed from boom at berth 6.
0950hrs | R. Archbald- Informed EMA updated of progress, they were informed of the boom breach.
0956hrs | C. Dyer: South-West of berth 6 boom snaged- oil breach. Calling out Security vessel and tug for mechanical dispersion if required.
1000hrs | Donald Harriram to be contacted by Ryan (HSE) to required scaffolding modification to access the snagged boom
1009hrs | Jens- Sheen of oil outside 40" containment boom
1010hrs | Randy requested to Jens that the boom at berth 6 adjusted.
1014hrs | S. Dyal requested 2 pirougues for mechanical dispersion. A vessel was previously dispatched and enroute.
1015hrs | Donald Harriram informed to scaffold modification request.